## Technical Enablement
Epic | User Story | Optional/Mandatory | Estimation | Amended Estimation | NEO impact | Comment
Foundation Configuration
| Cloud SQL (PostgreSQL) instance provisioning | M | S
| Middleware project scaffold and Cloud Run deployment pipeline | M | M
Content Model & Data Templates
| Collection Page | M | M
| Story Page | M | M
| Quiz page | M | M
| GTC Home Page | M | M
| GTC General Page | M | S |  |  | Can we reuse the Neo page?
Main Layout and Navigation
| Menu Navigation | M | M
| Header | M | M
| Hreflang & canonical tag implementation | M | S
| Footer | M | S
Publishing Workflow
| Publishing Workflow implementation | M | S |  |  | Most probably reusing the Neo workflow, Phrase integration support
Phrase Integration
| Support for multi-site Sitecore solutions, setting fallback language | M | L |  | We will reuse and modify NEO code | Editing workato flow script, storing data in db, providing support for new components
Cookies Consent integration
| Cookies Consent integration implementation | M | XS
Analytics
| GTM analytics integration | M | M
User Management
| IDP Authentication | M | M
| Login Page | M | XS |  |  | SSO page, just a redirect
| Partial Registraion | M | S
| Login, logout functionality | M | S
| New Registartion | M | XS |  |  | Just a link to the Neo Registration page
My Account
| API user's courses(get data from DB) | M | M
| My Completed Courses | M | M
Learning Progress Tracking
| Database schema implementation | M | M
| GTC Tracking Middleware implementation (course, chapter, quiz) | M | XL |  |  | APIs, data storing (quiz, chapters), dynamic unread module list injection
| Scroll-based chapter completion component (FE) | M | M
| Training completion status UI (module read indicators, quiz status, certificate CTA states) | M | M
Quiz Component
| Quiz component implementation | M | XL
| Question types implementation | M | XL
| Quiz progress tracking FE | M | M
| API for tracking and storing the answers | M | M
Certification Management
| Certificate Generation Middleware implementation | M | L |  |  | APIs, business logic, data storing
| Certificate PDF template implementation | M | M
Forms
| Feedback form | O | S
| Footer Form | O | S
| Middleware | O | M |  |  | APIs, transformations, queue for sending to Looker/DB/SMTP
Search
| Search Implementation | M | L
| Middleware | M | M |  |  | APIs, indexing logic, search output
Content Components
| Slideshow / Text Slider | O | M
| A/B Slider | O | M
| Accordion | O | S
| Image Tabs | O | M
| Hotspots | O | L
| Editorial Text | M | S
Looker Studio integration
| CSV import | O | M
| Learning Data Integration | O | L
Personalisation
| Personalization based on the Target Group implementation | M | L |  |  | Includes both component-level visibility (hide/show blocks per role) AND training list filtering by role availability, search functionality
Content editor roles and permissions
| Set up the roles and permissions | M | S
User Tracking Migration
| Learning Data Migration | M | XL
Content Migration
| Content Migration Automation | M | XL
| Content Migration per se | M | L
Launch
| URL structure definition per content type across 19 languages | M | M
| Sitemap generation and submission | M | S
| Redirects URL mapping delivery to NEO team | M | M
UAT & Quality Assurance
| E2E test suite (page types, quiz flows, tracking, forms, certificates) | M | L
| Accessibility audit (WCAG 2.1 AA) | O | M
| Cross-browser & cross-device testing | M | M
| Performance baseline (Core Web Vitals, Vercel, Cloud Run) | O | S
| Security review (JWT, Signed URLs, Middleware API, Cloud SQL) | M | M
| Content quality check (migrated content sign-off by GTC team) | M | M
| Monitoring - Vercel, middleware, website | M | S
Training & Handover
| Sitecore authoring training for GTC content editors | M | M
| Looker Studio dashboard walkthrough | O | S
| Handover to SoE for ongoing platform ownership | M | M
Go-Live & Cutover
| Cutover runbook with rollback plan | M | M
| DNS cutover for training.grohe.com | M | S
| Post-launch monitoring setup (Cloud Run, Cloud SQL, Vercel) | M | S
| Hypercare period (Actum on-call post-launch) | M | L
0
Enablement
R1
R2