## GTC Estimations
Ticket Name | T-shirt size | Req | DEV | QA | Total | Include | Assumptions | Total | 160
Foundation Configuration
CI/CD pipelines for Middleware | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository
Sitecore Multisite Configuration & GTC Site Setup | M | ✔️ | 4 | 1 | 5 | 0 | Multi-Site Solution and separate repository | [5 empty] | Total Estimations (hours)
Vercel multisite project configuration for GTC | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository | [5 empty] | BE | 128
GTC site definition in Sitecore | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Multi-Site Solution and separate repository | [5 empty] | FE | 32
Local dev environment setup for GTC developers | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository
CI/CD pipelines in Vercel for GTC project | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository
Cloud SQL (PostgreSQL) instance provisioning | S | ✔️ | 2.4 | 0.6 | 3 | 1
Middleware project scaffold and Cloud Run deployment pipeline | M | ✔️ | 4 | 1 | 5 | 1
Setting up the GCS instance | XS | 🚫 | 0.8 | 0.2 | 1 | 0 | we are using GTS for caching
Middleware
Define middleware API contract (OpenAPI / Swagger) - analysis | M | ✔️ | 4 | 1 | 5 | 0 | Platform Agnostic way
Apigee setup | S | ✔️ | 2.4 | 0.6 | 3 | 0 | We are using Apigee
Akami setup - CDN for assets, APIs caching | S | 🚫 | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution
Loabalancer setup | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Multi-Site Solution
Content Model & Data Templates
Collection Page | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Revise: Not multisite
Story Page | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Revise: Not multisite
Quiz page | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Revise: Not multisite
Data Items - Chapter, Course, Question, Menu Category | L | ✔️ | 8 | 2 | 10 | 0 | Data Items structure are used separately
GTC Home Page | M | ✔️ | 4 | 1 | 5 | 0 | NEO re-use
GTC General Page | S | ✔️ | 2.4 | 0.6 | 3 | 0 | NEO re-use
Main Layout and Navigation
Menu Navigation | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Revide the navigation and the way we can reuse the components from Neo
Header | M | ✔️ | 4 | 1 | 5 | 0 | Header is different
Hreflang & canonical tag implementation | XS | ✔️ | 0.8 | 0.2 | 1 | 1
Footer | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Footer is different
Publishing Workflow
Publishing Workflow implementation | S | ✔️ | 2.4 | 0.6 | 3 | 0 | GTC has it's own Workflow
Phrase Integration
Support for multi-site Sitecore solutions, setting fallback language | M | ✔️ | 4 | 1 | 5 | 1 | No Multi-Site, but new components supporting
Support for multi-site Sitecore solutions, setting fallback language | L | ✔️ | 8 | 2 | 10 | 0 | Multi-Site Soltion
Cookies Consent integration
Cookies Consent integration implementation | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Reusing the Neo
Analytics
GTM analytics integration | M | ✔️ | 4 | 1 | 5 | 1 | No custom actions and not too detailed |  |  | Revice with Marina: No complicated tracking
User Management
IDP Authentication | M | ✔️ | 4 | 1 | 5 | 0 | Multi-Site Soltion, Neo Tenant used
Login Page | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Neo Tenant used
Partial Registraion | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Reusing Neo and extending for GTC, Neo Tenant used
Login, logout functionality | S |  | 2.4 | 0.6 | 3 | 0 | Reusing Neo and extending for GTC, Neo Tenant used
APIs extension for GTC - multi tenant support | L | ✔️ | 8 | 2 | 10 | 0 | Multi-Site Soltion, Neo Tenant used
Header icon + dropdown menu | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion, Neo Tenant used
New Registartion | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Reusing Neo and extending for GTC, Neo Tenant used
My Account
Page template | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
User info | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
API user's courses(get data from DB) | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Send the completed cources data to Salesforce
My Completed Courses | M | ✔️ | 4 | 1 | 5 | 1
Learning Progress Tracking
Database schema implementation | M | ✔️ | 4 | 1 | 5 | 1
GTC Tracking Middleware implementation 1:1 from CRAFT | M | ✔️ | 4 | 1 | 5 | 1
GTC Tracking Middleware implementation platform-independent and granular | XL | ✔️ | 12 | 3 | 15 | 0 | Platform Agnostic way and granular
Scroll-based chapter completion component (FE) | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | Design needed | ✔️
Training completion status UI (module read indicators, quiz status, certificate CTA states) | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | Design needed | ✔️
Quiz Component
Quiz component implementation | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Design needed | ✔️
Question types implementation | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | Question types: multiple choice, true/false |  | ✔️
Quiz progress tracking FE | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Design needed | ✔️
API for tracking and storing the answers | M | ✔️ | 4 | 1 | 5 | 0 | Platform Agnostic way and granular
Certification Management
Certificate Generation Middleware implementation with GCP | L | ✔️ | 8 | 2 | 10 | 0 | we are using GTS for caching
Certificate Generation Middleware implementation with no GCP | M | ✔️ | 4 | 1 | 5 | 1
Certificate PDF template implementation | M | ✔️ | 4 | 1 | 5 | 1
Forms
Feedback form | S | 🚫 | 2.4 | 0.6 | 3 | 0 | Email send only |  |  | Sitecore Forms usage?
Footer Form | S | 🚫 | 2.4 | 0.6 | 3 | 0 | Email send only
Middleware | M | 🚫 | 4 | 1 | 5 | 0 | Email send only
Search
Search Implementation | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | Consider the recent Sacha's input | ✔️
Middleware | M | ✔️ | 4 | 1 | 5 | 0
Content Components
Slideshow / Text Slider | M | 🚫 | 4 | 1 | 5 | 0 | We can use the NEO slider |  |  | Design needed | Go the simplest way
A/B Slider | M | 🚫 | 4 | 1 | 5 | 1 |  |  |  | Design needed | Go the simplest way
Accordion | S | 🚫 | 2.4 | 0.6 | 3 | 0 | We can use the RTE to for the teaser |  |  | Design needed | Go the simplest way
Image Tabs | M | 🚫 | 4 | 1 | 5 | 0 | We map with a differnt component in NEO |  |  | Design needed | Go the simplest way
Hotspots | M | 🚫 | 4 | 1 | 5 | 1 |  |  |  | Design needed | Go the simplest way
Editorial Text | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Parralax effect is not needed |  |  | Design needed | Go the simplest way
Looker Studio integration
CSV import | M | 🚫 | 4 | 1 | 5 | 0 | We need CVS import
Learning Data Integration | M | 🚫 | 4 | 1 | 5 | 1 |  |  |  | To be revised based on the less complicataed approach | ✔️
Personalisation
Personalization based on the Target Group implementation | M | ✔️ | 4 | 1 | 5 | 1 |  |  |  | To be revided: consider the manual Target Group personalization mapping | ✔️
Content editor roles and permissions
Set up the roles and permissions | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | To be revised with ECM
User Tracking Migration
Learning Data Migration | XL | ✔️ | 12 | 3 | 15 | 0 | Platform Agnostic way and granular
Learning Data Migration 1:1 with CRAFT | S | ✔️ | 2.4 | 0.6 | 3 | 1
Content Migration
Content Migration Automation | L | ✔️ | 8 | 2 | 10 | 1 |  |  |  | Consider the manual assets migration | ✔️
Content Migration | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | Consider the manual assets migration | ✔️
Launch
URL structure definition per content type across 19 languages | M | ✔️ | 4 | 1 | 5 | 0 |  |  |  | Take a look into the details (multisite?)
Sitemap generation and submission | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution
Redirects URL mapping delivery to NEO team | S | ✔️ | 2.4 | 0.6 | 3 | 1
UAT & Quality Assurance
E2E test suite (page types, quiz flows, tracking, forms, certificates) | L | ✔️ | 8 | 2 | 10 | 0 | Full coverage |  |  | Consider less automated coverage
Accessibility audit (WCAG 2.1 AA) | S | 🚫 | 2.4 | 0.6 | 3 | 1 |  |  |  | Consider the less components we have | ✔️
Cross-browser & cross-device testing | M | ✔️ | 4 | 1 | 5 | 0
Performance baseline (Core Web Vitals, Vercel, Cloud Run) | S | 🚫 | 2.4 | 0.6 | 3 | 0
Security review (JWT, Signed URLs, Middleware API, Cloud SQL) | M | ✔️ | 4 | 1 | 5 | 0 | Multi-Site Soltion
Content quality check (migrated content sign-off by GTC team) | M | ✔️ | 4 | 1 | 5 | 0 |  |  |  | Consider the GTC team to check
Monitoring - Vercel, middleware, website | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
Training & Handover
Sitecore authoring training for GTC content editors | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | Consider the less components and smaller scope | ✔️
Looker Studio dashboard walkthrough | S | 🚫 | 2.4 | 0.6 | 3 | 0 | The dashboard is already exists and used by Grohe
Handover to SoE for ongoing platform ownership | M | ✔️ | 4 | 1 | 5 | 1
Go-Live & Cutover
Cutover runbook with rollback plan | S | ✔️ | 2.4 | 0.6 | 3 | 1 |  |  |  | Revise the number: the same infra | ✔️
DNS cutover for training.grohe.com | XS | ✔️ | 0.8 | 0.2 | 1 | 1 |  |  |  | Revise the number: the same infra | ✔️
Post-launch monitoring setup (Cloud Run, Cloud SQL, Vercel) | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
Hypercare period (Actum on-call post-launch) | L | ✔️ | 8 | 2 | 10 | 1
0
0
0
[6 empty] | 0 |  |  |  | QA revise = 80/20
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Assumptions
No Multisite solution is used. The GTC content to be incorporated into the NEO content tree. We are reusing same repository and same infrastructure.
No Google Could Storage is used storing Certificates. Google Cloud Run is used for temporary cache.
We are reusing the CRAFT database schema for storing the user learning process. Following the existing user progress storing logic.
Apigee setup is out of scope
We are reuing the Neo Header and Footer
We are reusing the NEO Content workflow
The GTM analytics integration is only standard, no complicated custom actions, etc.
CVS import is excluded. Direct Looker Studio connection used instead.
Components to be implemented: A/B Slider and Hotspots. Other components to be mapped wit the existing NEO ones
Personalization Rules to be developed in Sitecore but to be set up manually afterwards
Search is only extension of the NEO serarch: new section in the search dropdown + new Tab on the search results page
Question type to be used developed: multiple choice, true/false
IDP Authentication: the NEO tenant is used
We are not developing the platform agnostic API availabile for any other application

## Timeline
Epic | MD | April 2026 |  |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | July 2026
|  | W1 30 Mar - 03 Apr | W2 06 Apr - 10 Apr | W3 13 Apr - 17 Apr | W4 20 Apr - 24 Apr | W5 27 Apr - 01 May | W6 04 May - 08 May | W7 11 May - 15 May | W8 18 May - 22 May | W9 25 May - 29 May | W10 01 Jun - 05 Jun | W11 08 Jun - 12 Jun | W12 15 Jun - 19 Jun | W13 22 Jun - 26 Jun | W14 29 Jun - 03 Jul
Foundation (Cloud SQL + Middleware) | 8 |  | 8d
Content Model (Collection/Story/Quiz) | 15 | [5 empty] | 15d
Learning Progress Tracking | 16 |  |  | 16d
User Tracking Migration | 3 |  |  |  | 3d
Quiz Component & Question Types | 13 | [6 empty] | 13d
My Account & User Courses | 10 | [9 empty] | 10d
Content Migration (Automation + Run) | 13 | [5 empty] | 13d
Certification (Generation + PDF) | 10 |  |  |  | 10d
Search Implementation | 5 | [10 empty] | 5d
Content Components (A/B Slider, Hotspots) | 10 | [7 empty] | 10d
Looker Studio Integration | 5 | [9 empty] | 5d
Personalisation | 5 | [7 empty] | 5d
Roles & Permissions | 3 | [8 empty] | 3d
Navigation & Hreflang | 6 | [10 empty] | 6d
Phrase Integration | 5 | [10 empty] | 5d
Analytics (GTM) | 5 | [11 empty] | 5d
Launch (Redirects + SEO) | 3 | [11 empty] | 3d
UAT & Accessibility Audit | 3 | [11 empty] | 3d
Training & Handover | 8 | [12 empty] | 8d
Go-Live & Cutover (incl. Hypercare) | 14 | [13 empty] | 14d
TOTAL | 160