## GTC Estimations
Ticket Name | T-shirt size | Req | DEV | QA | Total | Include | Assumptions | Total | 138
Foundation Configuration
CI/CD pipelines for Middleware | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository
Sitecore Multisite Configuration & GTC Site Setup | M | ✔️ | 4 | 1 | 5 | 0 | Multi-Site Solution and separate repository |  |  | Total Estimations (hours)
Vercel multisite project configuration for GTC | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository |  |  | BE | 110.4
GTC site definition in Sitecore | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Multi-Site Solution and separate repository |  |  | FE | 27.6
Local dev environment setup for GTC developers | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository
CI/CD pipelines in Vercel for GTC project | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution and separate repository
Cloud SQL (PostgreSQL) instance provisioning | S | ✔️ | 2.4 | 0.6 | 3 | 1
Middleware project scaffold and Cloud Run deployment pipeline | M | ✔️ | 4 | 1 | 5 | 1
Looker Studio service in GCP | XS | 🚫 | 0.8 | 0.2 | 1 | 0 | we are using GTC for caching
Middleware
Define middleware API contract (OpenAPI / Swagger) - analysis | M | ✔️ | 4 | 1 | 5 | 0 | Platform Agnostic way
Apigee setup | S | ✔️ | 2.4 | 0.6 | 3 | 0 | We are using Apigee
Akami setup - CDN for assets, APIs caching | S | 🚫 | 2.4 | 0.6 | 3 | 0 | Multi-Site Solution
Loabalancer setup | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Multi-Site Solution
Content Model & Data Templates
Collection Page | M | ✔️ | 4 | 1 | 5 | 1
Story Page | M | ✔️ | 4 | 1 | 5 | 1
Quiz page | M | ✔️ | 4 | 1 | 5 | 1
Data Items - Chapter, Course, Question, Menu Category | L | ✔️ | 8 | 2 | 10 | 0 | Data Items structure are used separately
GTC Home Page | M | ✔️ | 4 | 1 | 5 | 1
GTC General Page | S | ✔️ | 2.4 | 0.6 | 3 | 1
Main Layout and Navigation
Menu Navigation | M | ✔️ | 4 | 1 | 5 | 0
Header | M | ✔️ | 4 | 1 | 5 | 0 | Header is different
Hreflang & canonical tag implementation | XS | ✔️ | 0.8 | 0.2 | 1 | 0
Footer | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Footer is different
Publishing Workflow
Publishing Workflow implementation | S | ✔️ | 2.4 | 0.6 | 3 | 0 | GTC has it's own Workflow
Phrase Integration
Support for multi-site Sitecore solutions, setting fallback language | M | ✔️ | 4 | 1 | 5 | 0 | No Multi-Site, but new components supporting
Support for multi-site Sitecore solutions, setting fallback language | L | ✔️ | 8 | 2 | 10 | 0 | Multi-Site Soltion
Cookies Consent integration
Cookies Consent integration implementation | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Reusing the Neo
Analytics
GTM analytics integration | M | ✔️ | 4 | 1 | 5 | 0 | No custom actions and not too detailed
User Management
IDP Authentication | M | ✔️ | 4 | 1 | 5 | 0 | Multi-Site Soltion
Login Page | XS | ✔️ | 0.8 | 0.2 | 1 | 1
Partial Registraion | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Reusing Neo and extending for GTC
Login, logout functionality | S | ✔️ | 2.4 | 0.6 | 3 | 1 | Reusing Neo and extending for GTC
APIs extension for GTC - multi tenant support | L | ✔️ | 8 | 2 | 10 | 0 | Multi-Site Soltion
Header icon + dropdown menu | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
New Registartion | XS | ✔️ | 0.8 | 0.2 | 1 | 0 | Reusing Neo and extending for GTC
My Account
Page template | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
User info | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
API user's courses(get data from DB) | M | ✔️ | 4 | 1 | 5 | 1
My Completed Courses | M | ✔️ | 4 | 1 | 5 | 1
Learning Progress Tracking
Database schema implementation | M | ✔️ | 4 | 1 | 5 | 1
GTC Tracking Middleware implementation 1:1 from CRAFT | M | ✔️ | 4 | 1 | 5 | 1
GTC Tracking Middleware implementation platform-independent and granular | XL | ✔️ | 12 | 3 | 15 | 0 | Platform Agnostic way and granular
Scroll-based chapter completion component (FE) | M | ✔️ | 4 | 1 | 5 | 1
Training completion status UI (module read indicators, quiz status, certificate CTA states) | M | ✔️ | 4 | 1 | 5 | 1
Quiz Component
Quiz component implementation | XL | ✔️ | 12 | 3 | 15 | 1
Question types implementation | XL | ✔️ | 12 | 3 | 15 | 1
Quiz progress tracking FE | M | ✔️ | 4 | 1 | 5 | 1
API for tracking and storing the answers | M | ✔️ | 4 | 1 | 5 | 0 | Platform Agnostic way and granular
Certification Management
Certificate Generation Middleware implementation with GCP | L | ✔️ | 8 | 2 | 10 | 0 | we are using GTC for caching
Certificate Generation Middleware implementation with no GCP | M | ✔️ | 4 | 1 | 5 | 1
Certificate PDF template implementation | M | ✔️ | 4 | 1 | 5 | 1
Forms
Feedback form | S | 🚫 | 2.4 | 0.6 | 3 | 0 | Email send only
Footer Form | S | 🚫 | 2.4 | 0.6 | 3 | 0 | Email send only
Middleware | M | 🚫 | 4 | 1 | 5 | 0 | Email send only
Search
Search Implementation | L | ✔️ | 8 | 2 | 10 | 0
Middleware | M | ✔️ | 4 | 1 | 5 | 0
Content Components
Slideshow / Text Slider | M | 🚫 | 4 | 1 | 5 | 0
A/B Slider | M | 🚫 | 4 | 1 | 5 | 0
Accordion | S | 🚫 | 2.4 | 0.6 | 3 | 0
Image Tabs | M | 🚫 | 4 | 1 | 5 | 0
Hotspots | L | 🚫 | 8 | 2 | 10 | 0
Editorial Text | S | ✔️ | 2.4 | 0.6 | 3 | 0
Looker Studio integration
CSV import | M | 🚫 | 4 | 1 | 5 | 0 | We need CVS import
Learning Data Integration | L | 🚫 | 8 | 2 | 10 | 0
Personalisation
Personalization based on the Target Group implementation | L | ✔️ | 8 | 2 | 10 | 0
Content editor roles and permissions
Set up the roles and permissions | S | ✔️ | 2.4 | 0.6 | 3 | 0
User Tracking Migration
Learning Data Migration | XL | ✔️ | 12 | 3 | 15 | 0 | Platform Agnostic way and granular
Learning Data Migration 1:1 with CRAFT | S | ✔️ | 2.4 | 0.6 | 3 | 1
Content Migration
Content Migration Automation | XL | ✔️ | 12 | 3 | 15 | 1
Content Migration | L | ✔️ | 8 | 2 | 10 | 1
Launch
URL structure definition per content type across 19 languages | M | ✔️ | 4 | 1 | 5 | 0
Sitemap generation and submission | S | ✔️ | 2.4 | 0.6 | 3 | 0
Redirects URL mapping delivery to NEO team | S | ✔️ | 2.4 | 0.6 | 3 | 0
UAT & Quality Assurance
E2E test suite (page types, quiz flows, tracking, forms, certificates) | L | ✔️ | 8 | 2 | 10 | 0
Accessibility audit (WCAG 2.1 AA) | M | 🚫 | 4 | 1 | 5 | 0
Cross-browser & cross-device testing | M | ✔️ | 4 | 1 | 5 | 0
Performance baseline (Core Web Vitals, Vercel, Cloud Run) | S | 🚫 | 2.4 | 0.6 | 3 | 0
Security review (JWT, Signed URLs, Middleware API, Cloud SQL) | M | ✔️ | 4 | 1 | 5 | 0 | Multi-Site Soltion
Content quality check (migrated content sign-off by GTC team) | M | ✔️ | 4 | 1 | 5 | 0
Monitoring - Vercel, middleware, website | S | ✔️ | 2.4 | 0.6 | 3 | 0 | Multi-Site Soltion
Training & Handover
Sitecore authoring training for GTC content editors | M | ✔️ | 4 | 1 | 5 | 0
Looker Studio dashboard walkthrough | S | 🚫 | 2.4 | 0.6 | 3 | 0 | The dashboard is already exists and used by Grohe
Handover to SoE for ongoing platform ownership | M | ✔️ | 4 | 1 | 5 | 0
Go-Live & Cutover
Cutover runbook with rollback plan | M | ✔️ | 4 | 1 | 5 | 0
DNS cutover for training.grohe.com | S | ✔️ | 2.4 | 0.6 | 3 | 0
Post-launch monitoring setup (Cloud Run, Cloud SQL, Vercel) | S | ✔️ | 2.4 | 0.6 | 3 | 0
Hypercare period (Actum on-call post-launch) | L | ✔️ | 8 | 2 | 10 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0