## Technical Enablement
Epic | User Story | Type | Dev Scope | Est. BE | Est. FE | Estimation | Comment
Foundation Configuration
CI/CD pipelines for Middleware
Sitecore Multisite Configuration & GTC Site Setup
Vercel multisite project configuration for GTC
GTC site definition in Sitecore
Local dev environment setup for GTC developers
CI/CD pipelines in Vercel for GTC project
Cloud SQL (PostgreSQL) instance provisioning
Middleware project scaffold and Cloud Run deployment pipeline
Content Model & Data Templates
Collection Page
Story Page
Quiz page
Data Items - Chapter, Course, Question, Menu Category
GTC Home Page
| GTC General Page | [5 empty] | Can we reuse the Neo page?
Main Layout and Navigation
Menu Navigation
Header
Footer
Publishing Workflow
| Publishing Workflow implementation | [5 empty] | Most probably reusing the Neo workflow
Phraze Integration
Phrase Integration implementation
Cookies Consent integration
Cookies Consent integration implementation
Analytics
GTM analytics integration
User Management
IDP Authentication
Login Page
Partial Registraion
| New Registartion | [5 empty] | Just a link to the Neo Registration page
My Account
My Account
My Completed Courses
Learning Progress Tracking
Database schema implementation
GTC Tracking Middleware implementation (course, chapter, quiz)
Scroll-based chapter completion component (FE)
Training completion status UI (module read indicators, quiz status, certificate CTA states)
Quiz Component
Quiz component implementation
Question types implementation
Quiz progress tracking FE
Certification Management
Certificate Generation Middleware implementation
Certificate PDF template implementation
Forms
Feedback form
Footer Form
Search
Search Implementation
Content Components
Slideshow / Text Slider
A/B Slider
Accordion
Image Tabs
Hotspots
Editorial Text
Looker Studio integration
Forms data integration
Learning Data Integration
Personalisation
| Personalization based on the Target Group implementation | [5 empty] | Includes both component-level visibility (hide/show blocks per role) AND training list filtering by role availability
Content editor roles and permissions
Set up the roles and permissions
User Tracking Migration
Learning Data Migration
Content Migration
Content Migration Automation
Content Migration per se
Launch
Domain finalization (training.grohe.com vs grohe.com/training)
URL structure definition per content type across 19 languages
Hreflang & canonical tag implementation
Metadata templates (title, description, OG) per content type
Sitemap generation and submission
Redirects URL mapping delivery to NEO team
UAT & Quality Assurance
E2E test suite (page types, quiz flows, tracking, forms, certificates)
Accessibility audit (WCAG 2.1 AA)
Cross-browser & cross-device testing
Performance baseline (Core Web Vitals, Vercel, Cloud Run)
Security review (JWT, Signed URLs, Middleware API, Cloud SQL)
Content quality check (migrated content sign-off by GTC team)
Training & Handover
Sitecore authoring training for GTC content editors
Looker Studio dashboard walkthrough
Middleware operational runbook (deployment, scaling, incident response)
Handover to SoE for ongoing platform ownership
Go-Live & Cutover
Cutover runbook with rollback plan
DNS cutover for training.grohe.com
Post-launch monitoring setup (Cloud Run, Cloud SQL, Vercel)
Hypercare period (Actum on-call post-launch)
Total complexity:
Enablement
R1
R2